**Schedule & Milestone**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| ID | Task name | Start | Finish | Duration |
| 01 | **Proposal** | 27/3/2015 | 30/3/2015 | 4 days |
| 02 | Survey & Overview | 27/3/2015 | 27/3/2015 | 1 day |
| 03 | Schedule & milestone | 28/3/2015 | 30/3/2015 | 2 days |
| 04 | **Requirement** | 1/4/2015 | 5/4/2015 | 5 days |
| 05 | User requirement Specification(URS) | 1/4/2015 | 3/4/2015 | 3 days |
| 06 | User requirement Specification(URS) | 4/4/2015 | 5/4/2015 | 2 days |
| 07 | **System design** | 7/4/2015 | 22/4/2015 | 16 days |
|  | Use case3 | 7/4/2015 | 9/4/2015 | 3 days |
| 08 | -Use case list | 7/4/2015 | 7/4/2015 | 1 day |
| 09 | - Use case diagram | 7/4/2015 | 7/4/2015 | 1 day |
| 10 | - Use case description | 8/4/2015 | 9/4/2015 | 2 days |
| 11 | Class diagram2 | 17/04/2015 | 18/4/2015 | 2 days |
| 12 | Sequence diagram2 | 18/4/2015 | 19/4/2015 | 2 days |
| 13 | The medthod design2 | 19/4/2015 | 20/4/2015 | 2 days |
| 14 | Activity diagram2 | 21/4/2015 | 22/4/2015 | 2 days |
| 15 | **Traceability Matrix** | 20/4/2015 | 22/20/2015 | 3 days |
| 16 | **Prototype** | 20/4/2015 | 22/4/2015 | 3 days |
| 17 | Web user interface | 20/4/2015 | 22/4/2015 | 3 days |
|  |  |  |  |  |

1.Proposal

1.1 Overview

1.2 Schedule & milestone

2.Requirement

2.1 User requirement Specification(URS)

2.2 System requirement Specification(SRS)

3.System design

3.1 Use case diagram

3.1.1 use case list

3.1.2 use case diagram

3.1.3 use case description

3.2 Class diagram

3.3 Sequence diagram

3.4 The method design

3.5 Activity diagram

4.Traceability Matrix

5.Prototype

5.1 Web user interface